Atmospheres of sub-Neptunes

Management Plan

Deadlines

The important immovable deadlines to plan around are:

- Seminar – 9th-13th March

- Final report – 27th March

Talking to the seminar lead resulted in the plan for the slides to be done for the beginning of week 7 results in the project being near completion during the beginning of week 6 giving sufficient time to create the seminar. Furthermore, the editors of the report were generally happy with the two weeks after the seminar to write the report with the idea of early drafts and progress being made while the project is ongoing.

Tasks

Group 1:

- Understand transmission spectrum code - In order to generate the spectra for different parameters and understand the prominent features. As well, read papers to decide what parameters to use for our atmosphere – based on what common sub-Neptune atmospheres consist of. This is aimed to be completed during week 1.

- Research JWST instruments - Identify functions of each of the JWST instruments and what they do best. JWST has four instruments, each with their own different modes. These cover specific wavelength ranges to varying spectral resolution. So each planet may be best observed by a specific instrument in a specific mode. This can be completed in parallel with the transmission spectrums in week 1.

- Atmospheric estimates - Estimate atmospheric composition for mean molecular weight. Similar to step 2, based on what common sub-Neptune atmospheres look like and use molecules that will give us well-defined peaks with no overlap.  This is a continuation of the transmission spectrums should be completed during week 2.

- Wavelength estimates - Pick a wavelength range for which feature we want to measure the height of. To do this we will identify at what wavelength there is a noticeable peak in absorption. This will depend on which or how many molecules are used in our atmospheric composition. Again, this can be completed in conjunction with the atmospheric estimates in week 2.

- Creating Simulations - simulate JWST spectrum for analysis group. Upload spectrum to PandExo which will generate JWST data points with associated errors. This will first be done for one test planet. This is one of the milestones of the project and a good indication of how progress is going. The target is these simulations be ready in week 3.

- Modify simulation code - Then can adapt the notebook to do multiple for variable inputs. Do it so that we don’t have to input all the parameters separately for each planet - especially when we have a lot of planets. The number depends on how many planets we get given from group 2. This will be a continuous task after the simulations are ready as the final targets are decided during the iterative process.

- Test atmospheric composition – If there is sufficient time, experiment with atmospheric composition. Don’t fit it make it variable?

Group 2

- Early target list – From the entire list of discovered exoplanets limit the search for potential targets to broad definitions of radius. Furthermore, only include planets with many known parameters including mass and radius of planet, stellar parameters and orbital period. This target is to be ready with a list of targets after group 1 is ready with the simulations.

- Final target list – Using the simulations from group 1, information from the research and the calculations of observation time and equilibrium temperature narrow the search to the final planets to focus on. This will start an iterative process after the early simulations are finished in week 3 with the aim of reducing to a final list in week 5.

- Researching – In order to help narrow the list of planets, research on the definition of sub-Neptunes, what makes a good target and the importance of future calculations will be done alongside the creation of the early target list. This will take place in parallel to an early target list and calculations on the targets with the aim of having a clear understanding by week 5.

- Observation Time – How long is needed on a target to obtain good data. Not crucial in the early target list but an important consideration when deciding how much total time is needed and the best allocation of that time for the final targets. A general function will be created to calculate the observation time for the large target list with the aim of having the observation time for all final targets done with the list by week 5.

- Equilibrium temperature – With one of the end goals being the creation of a graph that includes the equilibrium temperature, ensure the target list includes a range of temperatures is crucial. A function will be created to return the equilibrium temperature for a large selection of planets to inform which are included in the final list during week 4.

- Mapping spectrum peaks – A crucial step when determining how cloudy a given sub-Neptune is. The code for this will be produced in parallel to the other steps are being completed. This is because it is an important and complex step that needs to be accurate. The aim would be to have a generic mapping function by week 5 that can then be used on the simulations.

- Modelling and Statistical analysis – The final step in the project, with the simulated data of a range of sub-Neptunes and the ability to map the spectrum peaks to a given element, the data will be plotted and modelling to show any underlying relationship. This will include extensive statistical analysis to understand how clear the relationship is. This will take up the remaining time in the project before the week 6 deadline for the seminar preparation.

Milestones

To ensure this plan works as effectively as possible, aiming to reach these milestones as close to the target time as possible gives the project the best possible time of finishing on time.

- Work with one planet - Following the creation of the simulation code and an early list of potential targets ensure the communication and data flow between group 1 and 2 is effective by getting simulations of a single planet by the end of week 3.

- Targets, Simulations and Mapping – The final place to determining how the project is progressing. This is because the coding should be complete and subsequent steps are running the simulations for all the targets, finding peaks and modelling the tread of temperature and cloud using code already created.